Montview Stadium Case

Esmelinda A. Boadi

School of Business- 680, Liberty University

Author Note

Esmelinda A. Boadi

I have no known conflict of interest to disclose.

Correspondence concerning this article should be addressed to Esmelinda A. Boadi

Email: eaboadi@liberty.edu

The G&E Company intends to bid for the construction of 47,000 seat capacity Shoreline baseball stadium which must meet a completion deadline schedule of April 3, 2024, the opening date of the 2024 baseball season. Moreover, the construction commencement date is on July 1, 2020. Undesirably, there is a penalty clause of $100,000 per day of delay if the construction of the stadium does not meet the stipulated deadline (Larson & Gray, 2021).  Conceiving the benefits from the project, Percival Young, the president of the company is hopeful that the success of this project stands to sell the company in the long run while netting as much as $3 million on the present. Regardless of all these benefits, the company seeks to determine the feasibility of the project considering the conditions such as the schedule, activities, and costs surrounding the contract.

Project management as a practice involves planning, scheduling, executing, controlling, reporting, and closing the project successfully. To ensure successful completion, planning and scheduling is critical in construction projects because of the increasing complexities in the field of project management (Wali & Othman, 2019). For planning and scheduling work a huge amount of paperwork is required, which makes the construction management task more complicated. Managing a project such as Montview Stadium case comprises pre-construction planning to schedule the activities sequence, define labour tasks, construction methods and assigning the resources and responsibilities.

There are several techniques, tools, charts, and diagrams that are used for scheduling in project management. Apparently, Gantt Charts are the most common tools used for this purpose. A grant chart is a type of bar chart that illustrates project schedule. Gantt Charts are efficient tools to create a work schedule (Wali & Othman, 2019). Using Microsoft Project, Gantt Chart will be used to demonstrate the schedule for the Montview stadium construction project.

Will the project be able to be completed by the April 3rd deadline? How long will it take? How many working days are projected?

A thorough assessment of the requirements of the contract shows that the project is viable to be completed before the stipulated timeline because there is considerable amount of time to achieve success even with the exclusion of holidays and nonworking days of 31 days. This can be attained without making any stringent modification to the contract. Nonetheless, the probable risks associated with the project may have grave impact on the outcome of the project (Atin & Lubis, 2019). Risks such as machinery failure, labour agreement failures, unfavourable weather need to be critically assessed and provision made for to contain the severity of their effects on the project in order to ensure meeting the deadline.

What is the critical path for the project? List the activities on the critical path.

The critical path outlines the longest distance between the start and the end of a project (Atin & Lubis, 2019). It involves the path where delays may not occur in each project activity. Having been given the requirements and the material to be used on the roof, it is of opinion that the critical path for this project would fall to the construction of the roof and its inspection. This process during construction is the critical path because they have a significant impact on the nature and progress of the project, as it continues into the various sequential steps of construction (Ziółko, 2016). The critical paths for the project are 1-4-5-6-9-13-14-19. Based on the calculations in the updated case table 1, it can be concluded that the length of the critical path is estimated at 710 days.

Based on the schedule would you recommend that G&E pursue this contract? Why or why not?

Yes, in my opinion G&E should pursue this contract. I am basing this on the analysis acquired from the study on the critical path that shows the length for completion of the deadline to 710 days. Furthermore, G&E has all the resources needed for this project to be successful and completed before the established deadline, when considering the alternative critical paths. Between July 1, 2020 and April 3, 2024, there are 31 slack days that render G&E in a great position to meet the deadline and not accrue any penalties. Finally, a part from the expected profit of $3 million, G&E will also build a brand of value and reputation and potentially win more proposals in the future.

Summary

In conclusion, the critical area of attention is the activities and the amount of slack, hence, analysis of the success of the project must factor how much slack is in the project and what activities holds the greatest amount of slack. Consequently, during evaluation, caution is given to the activities with greatest amount of slack. This creates opportunity for working on other activities with less amount of slack concurrently (Larson & Gray, 2021). This move will create extra time for inspection while the construction is ongoing.

I recommend that the company undertakes the project in three main activities at the beginning of the Shoreline Stadium Project. The activities include demolishing the building, the pouring of the lower concrete bowl, and the installation of the roof. These three activities are major determinants because their completion will mark the start of subsequent activities for at least 6 other activities outline in the stadium schedule. Also, fast tracking and crash duration are important in attaining the completion date faster. However, while fast tracking reduces project timeframe, it comes with risk due to performing parallel activities that were hitherto planned to be performed in sequence. Similarly, crashing the critical path may result in lower quality of work because the goal in crash duration is speed.

Appendix 1

| Risk Event | Response | Contingency Plan | Trigger | Who is responsible |
| --- | --- | --- | --- | --- |
| Unfavourable weather (Colder December) | Retaining | Special heating adaptation | Change in weather/ Winter | Team members |
| Possible labour strike | Mitigating | Renegotiation of agreement | Labour agreement expires/ Complains from labourers | Project manager/ Top management |
| Machinery breakdown | Transferring | Work around until experts’ support arrive | When construction equipment malfunctions | Equipment experts |

Table 1: Risk Response Matrix

References

Atin, S., & Lubis, R. (2019, November). Implementation of Critical Path Method in Project Planning and Scheduling. In IOP Conference Series: Materials Science and Engineering, 662(2), p. 022031. IOP Publishing.

Larson, E. W., & Gray, C. F. (2021). Project management: The managerial process (8th ed.). McGraw-Hill.

Wali, K. I., & Othman, S. A. (2019). Comparison and Assessment of Using Primavera and Microsoft Project in Construction Projects in Erbil City. Zanco Journal of Pure and Applied Sciences, 31(s3), 285-291.

Ziółko, J. (2016). Assembly of the steel roof structure for the football stadiums in the United States. Steel Construction, 6(1), 54-60. doi:10.1002/stco.2016147897