## Milestone Table
Google's Expansion Project
START DATE
2021-01-01
[6 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | YEAR FOUR | [11 empty] | YEAR FIVE | [11 empty] | DO NOT ALTER CELL BELOW
[6 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y4Q1 |  |  | Y4Q2 |  |  | Y4Q3 |  |  | Y4Q4 |  |  | Y5Q1 |  |  | Y5Q2 |  |  | Y5Q3 |  |  | Y5Q4
PROJECT NAMES + TASK TITLES | START DATE | END DATE | Responsible Party | # of Days | % Completion | [60 empty] | 2026-01-01 | time axis 2021-01-01 to 2025-12-01
 | time axis 2021-01-01 to 2025-12-01
Project Initiation | 2021-01-05 | 2022-04-21 |  | 338 | bar: 2021-01-01 to 2025-12-01
Needs assessment | 2021-01-05 | 2021-05-05 | Project Manager | 87 | 10% | bar: 2021-01-01 to 2021-05-01
Gap analysis | 2021-04-02 | 2021-08-31 | Project Manager | 108 | 20% | bar: 2021-04-01 to 2021-08-01
Goal setting | 2021-07-11 | 2021-10-15 | Project Manager | 70 | 0% | bar: 2021-07-01 to 2021-10-01
Define deliverables | 2021-10-01 | 2021-12-31 | Project Manager | 66 | 0% | bar: 2021-10-01 to 2021-12-01
Create project schedule | 2021-01-05 | 2022-03-11 | Project Manager | 309 | 0% | bar: 2021-01-01 to 2022-03-01
Financial analysis | 2022-03-12 | 2022-04-21 | Financial Analyst | 29 | 0% | bar: 2022-03-01 to 2022-04-01
Project Planning | 2021-04-22 | 2022-08-15 |  | 343 | 0% | bar: 2021-01-01 to 2025-12-01
Identify and meet potential stakeholders | 2021-04-22 | 2021-09-21 | Project manager | 109 | 0% | bar: 2021-04-01 to 2021-09-01
Market segmentation | 2021-05-30 | 2021-11-02 | Marketing department | 112 | 0% | bar: 2021-05-01 to 2021-11-01
Develop product positioning | 2021-08-05 | 2021-12-19 | Marketing department | 97 | 0% | bar: 2021-08-01 to 2021-12-01
Investigate segmentation bases | 2021-10-25 | 2021-10-31 | Marketing department | 5 | 0% | bar: 2021-10-01
Develop risk analysis | 2021-10-25 | 2022-03-26 | Industry consultant | 110 | 0% | bar: 2021-10-01 to 2022-03-01
Prepare project charter | 2021-12-01 | 2022-08-15 | Project manager | 184 | 0% | bar: 2021-12-01 to 2022-08-01
Project Execution | 2022-02-14 | 2023-10-14 |  | 435 | 0% | bar: 2021-01-01 to 2025-12-01
Meet project stakeholders | 2022-02-14 | 2022-02-28 | Project manager | 11 | 0% | bar: 2022-02-01
Communicate project plan to stakeholders | 2022-02-28 | 2022-06-28 | Project manager | 87 | 0% | bar: 2022-02-01 to 2022-06-01
Acquire talent | 2022-03-02 | 2022-06-28 | HR | 85 | 0% | bar: 2022-03-01 to 2022-06-01
Recruit vendors | 2022-06-28 | 2022-07-11 | Procurement Department | 10 | 0% | bar: 2022-06-01 to 2022-07-01
Build technology infrastructure | 2022-07-14 | 2023-09-14 | IT Team | 306 | 0% | bar: 2022-07-01 to 2023-09-01
Execute marketing activities | 2023-09-15 | 2023-10-14 | Marketing department | 21 | 0% | bar: 2023-09-01 to 2023-10-01
Performance Monitoring | 2024-03-01 | 2025-07-28 |  | 367 | 0% | bar: 2021-01-01 to 2025-12-01
Review project performance | 2024-12-01 | 2025-07-28 | Project manager | 171 | 0% | bar: 2024-12-01 to 2025-07-01
Monitor performance against benchmarks | 2024-03-01 | 2024-03-31 | Project team | 21 | 0% | bar: 2024-03-01
Identify potential problems | 2024-03-25 | 2024-11-01 | Project team | 160 | 0% | bar: 2024-03-01 to 2024-11-01
Determine recommendations and suggestions | 2024-06-22 | 2024-12-21 | Project stakeholders | 130 | 0% | bar: 2024-06-01 to 2024-12-01
Implement suggestions | 2024-09-30 | 2025-03-04 | Project manager | 112 | 0% | bar: 2024-09-01 to 2025-03-01
Implement internal control performance measures | 2024-12-01 | 2025-05-06 | Project manager | 112 | 0% | bar: 2024-12-01 to 2025-05-01
Project Close | 2025-02-20 | 2025-12-22 |  | 218 | 0% | bar: 2021-01-01 to 2025-12-01
Confirm project completion | 2025-02-20 | 2025-05-26 | Project Sponsor | 68 | 0% | bar: 2025-02-01 to 2025-05-01
Review contracts and documentation | 2025-04-12 | 2025-05-30 | Project Manager | 35 | 0% | bar: 2025-04-01 to 2025-05-01
Notify stakeholders about project completion | 2025-06-14 | 2025-06-28 | Project Manager | 10 | 0% | bar: 2025-06-01
Conduct performance review of the project | 2025-07-02 | 2025-07-28 | Project Manager | 19 | 0% | bar: 2025-07-01
Review lessons learned | 2025-07-30 | 2025-09-22 | Project Manager | 39 | 0% | bar: 2025-07-01 to 2025-09-01
Archive documentation | 2025-12-01 | 2025-12-22 | Project Manager | 16 | 0% | bar: 2025-12-01