## Case 13.1 Tree Trimming Project
Number of Douglas Fir Christmass Tree | 24000
Contract Lump some with the crew boss | 30000 | % out of total number of Douglas Fir Christmass tree in the field | 25
Actual number sheared after 5 days | 6000 | % out of total agreed contract sum with crew boss | 25
5 days work complete partial payment (0.25 *$30,000) | 7500

## Appendix exercise 2
Shedule information | [6 empty] | Baseline Budget Needs
EV rule | ACT/WP | DUR | ES | LF | SL | Total PV | Time period
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
2 | 1 | 3 | 0 | 5 | 2 | 30 | Time period 1: 15; Time period 3: 15
3 | 2 | 2 | 0 | 3 | 1 | 20
2 | 3 | 4 | 0 | 4 | 0 | 30 | Time period 1: 15; Time period 4: 15
3 | 4 | 2 | 3 | 7 | 2 | 10 | Time period 5: 10
2 | 5 | 4 | 2 | 7 | 1 | 40 | Time period 3: 20; Time period 6: 20
1 | 6 | 3 | 4 | 7 | 0 | 30 | Time period 5: 17; Time period 6: 3; Time period 7: 10
1 | 7 | 3 | 7 | 10 | 0 | 60 | Time period 7: 20; Time period 8: 30; Time period 9: 10
Total PV by period | [6 empty] | 30 | 20 | 35 | 15 | 27 | 23 | 30 | 30 | 10
Cumulative PV by period | [6 empty] | 30 | 50 | 85 | 100 | 127 | 150 | 180 | 210 | 220
Variances calculation
Task | Final % complete | Budget PV | EV | AC | PV | CV | bar: Time period 1
End of period 4
1 | 1 | 12 | 12 | 13 | 12 | 156 | Time period 1: 144
2 | 1 | 15 | 15 | 18 | 15 | 270 | Time period 1: 225
3 | 1 | 8 | 8 | 10 | 8 | 80 | Time period 1: 64
4 | 1 | 6 | 6 | 8 | 6 | 48 | Time period 1: 36
5 | 0.3 | 10 | 3 | 3 | 6 | 9 | Time period 1: 18
6 | 0.667 | 9 | 6.003 | 8 | 6 | 48.024 | Time period 1: 36.018
7 | 0 | 5 | 0 | 0 | 0 | 0 | Time period 1: 0
Cummulative |  |  | 50.003 | 60 | 53 | 611.024 | Time period 1: 523.018
Periodic Status Report
Status Report ending Period 1
Task | % complete | Budget PV | EV | AC | PV | CV | bar: Time period 1
1 | 40% | 30 | 15 | 8 | 15 | 7 | Time period 1: 0
2 | 0% | 20 | 0 | 12 | 0 | -12 | Time period 1: 0
3 | 30% | 30 | 15 | 10 | 15 | 5 | Time period 1: 0
Cumulative total |  |  | 30 | 30 | 30 | 0 | Time period 1: 0
Project Status: Ending Period 2
1 | 80% | 30 | 15 | 20 | 15 | -5 | Time period 1: 0
2 | 100% | 20 | 20 | 18 | 20 | 2 | Time period 1: 0
3 | 50% | 30 | 15 | 12 | 15 | 3 | Time period 1: 0
Cumulative total |  |  | 50 | 50 | 50 | 0 | Time period 1: 0
Project Status: Ending Period 3
1 | 100% | 30 | 30 | 27 | 30 | 3 | Time period 1: 0
2 | 100% | 20 | 20 | 18 | 20 | 2 | Time period 1: 0
3 | 70% | 30 | 15 | 15 | 15 | 0 | Time period 1: 0
4 | 0% | 10 | 0 | 5 | 0 |  | Time period 1: 0
5 | 30% | 40 | 20 | 8 | 20 | 12 | Time period 1: 0
Cumulative total |  |  | 85 | 73 | 85 | 17 | Time period 1: 0
Project Status: Ending Period 4
1 | 100% | 30 | 30 | 27 | 30 | 3 | Time period 1: 0
2 | 100% | 20 | 20 | 18 | 20 | 2 | Time period 1: 0
3 | 100% | 30 | 30 | 22 | 30 | 8 | Time period 1: 0
4 | 0% | 10 | 0 | 7 | 0 | -7 | Time period 1: 0
5 | 60% | 40 | 20 | 22 | 20 | -2 | Time period 1: 0
Cumulative total |  |  | 80 | 96 | 100 | 6 | Time period 1: 0
Project Status: Ending Period 5
1 | 100% | 30 | 30 | 27 | 30 | 3 | Time period 1: 0
2 | 100% | 20 | 20 | 18 | 20 | 2 | Time period 1: 0
3 | 100% | 30 | 30 | 22 | 30 | 8 | Time period 1: 0
4 | 100% | 10 | 10 | 8 | 10 | 2 | Time period 1: 0
5 | 70% | 40 | 28 | 24 | 20 | 4 | Time period 1: 8
6 | 30% | 30 | 9 | 10 | 17 | -1 | bar: Time period 1
Cumulative total |  |  | 127 | 109 | 127 | 18 | Time period 1: 0
Schedule performance index and cost performance index
Period | EV | AC | PV | SPI | CPI | PCIB
1 | 30 | 30 | 30 | 1 | 1 | 0.3
2 | 30 | 30 | 30 | 1 | 1 | 0.3
3 | 85 | 73 | 85 | 1 | 1.1644 | 0.85
4 | 80 | 96 | 100 | 0.8 | 0.83333 | 0.8
5 | 127 | 109 | 127 | 1 | 1.1651 | 1.27
Index Period 1-5 Graph | [5 empty] | Project Status progress by end 5